## Community Engagement Plan
Id | Category | Title | Objective | Phase | Target artefacts | Target groups | Disseminaiton materials | Evaluation mechanisms | Outcomes | Location | Date | Responsible
W1 | WORK WITH | Static sensors installation in Etopia | Installing static sensors to improve data quality | Pre- Pilot | GREENGAGE sensors and platform components | Bee-keepers | Documentation of the process |  |  | Etopia | 2023-12-23 | Bee-keepers: Pilar Martín, Daniel Lisbona, Carlos Lopez, Ana Jimenez
I1 | INFORM | Internal testing workshop | Deployment of GREENGAGE platform, toolkit, knoweldge base and instantiation of test campaigns in Pilot | Pre-pilot | GREENGAGE platform components, communication materials and evaluation mechanisms | Bee-keepers | Communication material and evaluation mechanisms | Alpha Questionnaires | Alpha Questionnaires | Etopia | dic 23 / jan 24 | Bee-keepers: Pilar Martín, Daniel Lisbona, Carlos Lopez, Ana Jimenez
W2 | WORK WITH | Campaigns design meeting | Design the second pilot iteration campaigns | Pre-pilot | GREENGAGE platform components, engagement materials | Bee-keepers | GREENGAGE campaigns templates |  |  | Etopia | dic 23 / jan 24 | Bee-keepers: Pilar Martín, Daniel Lisbona, Carlos Lopez, Ana Jimenez
I2 | INFORM | Open call for schools preparation | Design the open call for schools | Pre- Pilot | GREENGAGE platform components, communication materials and evaluation mechanisms | Schools | Communication and engagement material |  |  | Etopia | jan 24 | Bee-keepers: Pilar Martín, Daniel Lisbona, Carlos Lopez, Ana Jimenez
I3 | INFORM | Creation of the communication Plan | Announcement of GREENGAGE pilot and purpose (press release, social media posts) among alpha testers | Pre- Pilot | GREENGAGE communication materials | citizens | Communication and engagement material |  |  | On-line | jan 24 | Bee-keepers: Pilar Martín, Daniel Lisbona, Carlos Lopez, Ana Jimenez
I4 | INFORM | open call launch for schools | Opening of the open call for schools. | Pilot | GREENGAGE communication materials | Schools | Terms and conditions of the call for applications |  |  | On-line | jan 24 | Bee-keepers: Pilar Martín, Daniel Lisbona, Carlos Lopez, Ana Jimenez
C1 | CONSULT | Schools recruitment period | Application period and answers to doubts | Pilot | GREENGAGE communication materials | Schools | Terms and conditions of the call for applications |  |  | On-line | Jan - Mar 24 | Bee-keepers: Pilar Martín, Daniel Lisbona, Carlos Lopez, Ana Jimenez
W3 | WORK WITH | Campaigns with schools | Get data about Air Quality, Complete the science loop in the classroom | Pilot | GREENGAGE platform components, communication materials and evaluation mechanisms | Schools | Communication and engagement material | Questionnaires | Questionnaires | XXX | Apr-May 24 | Beekeepers and Queen Bees.
W4 | WORK WITH | Meetings with AGZ air quality hive | Working in the Citizen science and engagement part of the project with the hive members | Pilot | GREENGAGE platform components, engagement materials | citizens | data review, campaigns and evaluations mechanisms |  |  | Etopia | Apr-May 24 | Bee-keepers: Pilar Martín, Daniel Lisbona, Carlos Lopez, Ana Jimenez
I5 | INFORM | Dissemination activities and workshops with XXX hive | Communicate the results and reach local institutions | Pilot | GREENGAGE results | citizens | Communication and engagement material |  |  | Online / Etopia | Jan - Jun 24 | Bee-keepers: Pilar Martín, Daniel Lisbona, Carlos Lopez, Ana Jimenez
W5 | WORK WITH | Local Campaingns | Working in the Citizen science and engagement part of the project with the hive members | Pilot | GREENGAGE platform components, engagement materials | Bee-keepers / AGZ | Communication and engagement material | Questionnaires | Questionnaires | Etopia | Jan - Jun 24 | Beekeepers, Queen Bees, Bees and drones.
G1 | GUIDE | Supervision meetings with all the hives | Review air quality data, complete the scientific hive loop. | Pilot | GREENGAGE data | Bee.Keepers / School | data review, campaigns and evaluations mechanisms |  |  | Online / School | Apr-May 24 | Bee-keepers: Pilar Martín, Daniel Lisbona, Carlos Lopez, Ana Jimenez
W6 | WORK WITH | Others campaings with institutions and partnerships | Working in the Citizen science and engagement part of the project with the hive members | Pilot | GREENGAGE platform components, engagement materials | citizens | Communication and engagement material | Questionnaires | Questionnaires | XXX | Apr-May 24 | Bee-keepers: Pilar Martín, Daniel Lisbona, Carlos Lopez, Ana Jimenez
I6 | INFORM | Final event | Communicate the results | Pilot | GREENGAGE results | citizens | Communication materials and data results | Results and hypothesis |  | Etopia | 2023-06-24 | Bee-keepers: Pilar Martín, Daniel Lisbona, Carlos Lopez, Ana Jimenez
C2 | CONSULT | Dissemination of results activities | Communicate the results | Pilot | GREENGAGE results | citizens | Communication materials and data results | Results and hypothesis |  | Online / Etopia | 2023-06-24 | Bee-keepers: Pilar Martín, Daniel Lisbona, Carlos Lopez, Ana Jimenez

## Categories
Category | Evaluation mechanisms
INFORM | Activities to create awareness using traditional communication methods and channels. Within this type of activity, communication materials must be ready for pre- and pilot execution subphases.
GUIDE | Activities to assists end-user stakeholders and give them guidance for how to use the GREENGAGE platform. Within this type of activity, training materials, HOW-TOs to support pilot owners, and support mechanisms are made available.
CONSULT | Activities to obtain end-user stakeholders’ feedback on the GREENGAGE platform and associated citizen science campaigns. For it, questionnaires, focus group sessions, cross-testing sessions, and interviews are used.
WORK WITH | Activities which consider end-user stakeholders’ concerns and aspirations on the GREENGAGE platform and Citizen Science. Their objective is not only to involve users but also to empower them to partake with support tools and guidelines. Such activities are supported by GREENGAGE platform and toolkit designed to aid planning, execution, and evaluation of campaigns.
This document is published under a Creative Commons Attribution-ShareAlike 4.0 International License, 2024, GREENGAGE project