## Workplan
ID | Milstone (MS) | GO phases | GO sub-phases | When | Action | Measurement mechanism | Description | Target | Comments
IR1 | 1 | Preparing | Preparing-ThemeSelection |  | Internal release |  | Deployment of GREENGAGE platform, toolkit, knoweldge base and instantiation of test campaigns in Pilot | Alpha testers: public servants, | Whatever needed
C1.1 | 1 | [5 empty] | Announcement of GREENGAGE pilot and purpose (press release, social media posts) among alpha testers
C1.2 | 1 | [5 empty] | Workshop with potential alpha testers informing about purpose, privacy procedures and policies
T2.1 | 2 | [5 empty] | Training of pilot owner representatives about GREENGAGE support system
T2.2 | 2 | [5 empty] | Physical and/or online workshop about GREENGAGE platform and GO's thematic co-exporations
S2.1 | 2 | [5 empty] | Address in a timely manner (within 2 business days) issues related to usage of GREENGAGE assets
S2.2 | 2 | [5 empty] | Populate FAQ and lessons learnt catalogue with common questions and support requests received in piloting
MM2.1 | 2 | [5 empty] | Guidelines with usage scenario for Pilot case produced
MM2.2 | 2 | [5 empty] | Cross-testing workshop
MM2.3 | 2 | [5 empty] | Internal testing workshop
MM2.4 | 2 | [5 empty] | Alpha questionnaire issued to gather feedback from alpha testers
MM2.5 | 2 | [5 empty] | Verification pilot associated logs and questionnaires are correctly gathered
ER2 | 2 | [5 empty] | External release of GREENGAGE platform and citizen science campaigns, knowledge base and toolkit
C3.1 | 2 | [5 empty] | Announcement of pilot public start
C3.2 | 2 | [5 empty] | Public training presentation for interested civil servants and citizens
S3.1 | 2 | [5 empty] | Address in a timely manner (within 2 business days) issues related to usage of GREENGAGE assets
S3.2 | 2 | [5 empty] | Enhance pilot documentation, materials and FAQ
EX3.1 | 2 | [5 empty] | Engaging material to prepare quiz/gamified description of challenge to be addressed by users online
EX3.2 | 2 | [5 empty] | Workshop with public servants to organize challenge / contest about improving co-designed citizen science experiments
EV3.1 | 2 | [5 empty] | Monthly review of progress of pilot: analysis of KPIs, logs and questionnaires
R3 | 2 | [5 empty] | Monthly new actions will be taken to enhance the testing experience and maximize outcomes of the process
EV3.2 | 3 | [5 empty] | Generation of final evaluation report
Legend
[8 empty] | IR | Internal Release
[8 empty] | C | Communication
[8 empty] | T | Training
[8 empty] | S | Support
[8 empty] | MM | Measuring and Monitoring
[8 empty] | ER | External release
[8 empty] | EX | Execution
[8 empty] | EV | Evaluation
[8 empty] | R | Reaction
This document is published under a Creative Commons Attribution-ShareAlike 4.0 International License, 2024, GREENGAGE project

## Categories
Action type | Comment | GO phases | GO phases | Who will do what | Comment | Target group | Phases | Milestones | Description
IR | Stands for Internal Release | Preparing | Preparing-ThemeSelection |  |  |  |  | 1 | Milestone 1 (MS) – Pre-pilot launch subphase (M13 – January 2024 to M14 – Feb 2024).
C | Communication | Designing | Preparing-PilotOwnersTraining |  |  |  |  | 2 | Milestone 2 (MS) – Pilot execution sub-phase (M15 – Mar 2024 to M17 – May 2024).
T | Training | Experimenting | Preparing-CoreTeamOnboarding |  |  |  |  | 3 | Milestone 3 (MS) – Post-Pilot execution sub-phase (M18 – June 2024 ).
S | Support | Sharing | Preparing-CoreTeamTraining
MM | Measuring & Monitoring |  | Designing-ExperimentSpecification
ER | External Release |  | Designing-ToolsResourcesSelection
S | Support |  | Designing-ToolsResourcesCustomization
E | Execution |  | Designing-ToolsResourcesTesting
M | Monitoring |  | Experimenting-ObserversOnboarding
EX | Execution |  | Experimenting-ObserversTrainingSupport
EV | Evaluation |  | Experimenting-DataCollection
R | Reaction |  | Experimenting-DataCombination
Experimenting-DataAnalysis
Experimenting-DataVisualization
Experimenting-Evaluation
Sharing-Storytelling
Sharing-PolicyAdvocacy
Sharing-Sustainability

## Discourse
Tags | Categories associated | Phases | Categories | Objectives | Sub-categories
Internal Release |  | Preparing | Preparing | Preparing-ThemeSelection | Theme selection | Preparing
Communication |  | Designing | Designing | Preparing-PilotOwnersTraining | Pilot owners training
Training |  | Experimenting | Experimenting | Preparing-CoreTeamOnboarding | Core team onboarding
Support |  | Sharing | Sharing | Preparing-CoreTeamTraining | Core team training
Measuring & Monitoring |  |  |  | Designing-ExperimentSpecification | Experiment specification | Designing
External Release |  |  |  | Designing-ToolsResourcesSelection | Tools and resources selection
Support |  |  |  | Designing-ToolsResourcesCustomization | Tools and resources customization
Execution |  |  |  | Designing-ToolsResourcesTesting | Tools and resources testing
Monitoring |  |  |  | Experimenting-ObserversOnboarding | Observers onboarding | Experimenting
Execution |  |  |  | Experimenting-ObserversTrainingSupport | Observers training and support
Evaluation |  |  |  | Experimenting-DataCollection | Data collection
Reaction |  |  |  | Experimenting-DataCombination | Data combination
Engagement |  |  |  | Experimenting-DataAnalysis | Data analysis
Data capture |  |  |  | Experimenting-DataVisualization | Data visualization
Data curation |  |  |  | Experimenting-Evaluation | Experiment evaluation
Data analysis |  |  |  | Sharing-Storytelling | Findings storytelling | Sharing
Data visualization |  |  |  | Sharing-PolicyAdvocacy | Translation into policies
Scientific method |  |  |  | Sharing-Sustainability | Experiment sustainability
Sustainability